## Special
Special Programme for Development of Infrasructure - 2019 | [17 empty] | Annexure - 2
Physical and Financial Progress of the Month of 30 NOVEMBER 2019
District -GALL |  |  |  | ELPITIYA -
No | Name of the Project |  | DS Division | GN Division | Sector * | Name of Minister / Member of Parliament/ Officer who proposed the project | Length/Area (m./k.m./sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No. of Beneficiaries | Remarks
[11 empty] | Financial |  | Physical **
[11 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[14 empty] | B1 | B2 | B3 | B4
1 | CONSTRUCTING THE MULLEGADERA ROAD OF REKADA HENA | රෑකඩහේන මුල්ලෙගෙදර පාර කොන්ක්‍රීට් කිරිම | ELPITIYA | REKADAHENA | RA | HON. GAYANTHA KARUNATHILAKA | leanth 79 m - width 2.43m | 0.5 | DIVISIONAL SECRETARIAT-ELPITIYA | GRAMASANWARDANA SOCIETY - REKADAHENA | 0.495 | [10 empty] | 1 | 125
2 | CONSTRUCTING THE MORAKANDA ROAD OF REKADA HENA | රෑකඩහේන මොරකන්ද පාර කොන්ක්‍රීට් කිරිම | ELPITIYA | REKADAHENA | RA | HON. GAYANTHA KARUNATHILAKA | leanth 87m -width 2.1 | 0.5 | DIVISIONAL SECRETARIAT-ELPITIYA | GRAMASANWARDANA SOCIETY - REKADAHENA | 0.495 | [10 empty] | 1 | 175
3 | THARRING ROAD OF MITHREE WELFARE SOCITY AT BATUWANHENA | බටුවන්හේන රජමහා විහාරමාවතේ මෛත්‍රී සුභසාධක සමිතියට යන පාර තාර දැමීම | ELPITIYA | BATUWANHENA | RA | HON. GAYANTHA KARUNATHILAKA |  | 0.5 | DIVISIONAL SECRETARIAT-ELPITIYA | GRAMASANWARDANA SOCIETY - REKADAHENA | 0.414 | [10 empty] | 1 | 200
4 | CONCRETING OF JAYANTHI MAWATHA AT IGALA | ඉගල ජයන්ති මාවත කොන්ක්‍රීට් කිරිම | ELPITIYA | IGALA | RA | HON. GAYANTHA KARUNATHILAKA |  | 1 | DIVISIONAL SECRETARIAT-ELPITIYA | [9 empty] | 1 |  |  |  | 125
5 | WATER SUPPLY AT BULUGAHAHANDIYA OMATHA | ඕමත්ත බුළුගහහන්දිය ජල සැපයුම ලබාදිම | ELPITIYA | 28 C OMATHTHA | WS | HON. GAYANTHA KARUNATHILAKA |  | 1 | DIVISIONAL SECRETARIAT-ELPITIYA |  | 0.99751 | [10 empty] | 1 | 120 | ප්‍රජා ජල සැපයුම් දෙපාර්තමේන්තුව වෙත මුදල් නිදහස් කර ඇත
6 | REHABILITATION OF CHANNEL AT BERUGODAWELA | ඕපාත බේරුගොඩ වෙල ඇල ප්‍රතිසංස්කරණය | ELPITIYA | OPATHA | WS | HON. GAYANTHA KARUNATHILAKA |  | 1 | DIVISIONAL SECRETARIAT-ELPITIYA | [9 empty] | 1 |  |  |  | 165
[8 empty] | 4.5 |  |  | 2.4015 | [6 empty] | 0 | 2 |  |  | 4 | 910
* Projects should be categorized for following sectors |  |  |  |  | ** Physical progress
WS - Rural Water Supply |  |  |  |  | A - Estimates are being / to be prepared
RA - Rural Access |  |  |  |  | B - For Constructions : B-1- Estimates Approved & Bid Documents Prepared, B-2- Quotation / Bid called, B-3- Quotation / Bid Received , B-4- Contract Awarded
EI - Economic Infrastructure |  |  |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimate prepared
RE - Rural Economy |  |  |  |  | C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
SW - Social Welfare |  |  |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
EL - Rural Electricity |  |  |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
PW - Public Welfare |  |  |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
OI - Other Infrastructure |  |  |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs